## Business Plan
ID | Project Name | Owner | Days | Start | End | 2024-09-17
1 | Marketing Research Tactical Plan | J. Dow | 70 | 2024-07-09 | 2024-09-17
1.1 | Scope Definition Phase | J. Dow | 10 | 2024-07-09 | 2024-07-19
1.1.1 | Define research objectives | J. Dow | 3 | 2024-07-09 | 2024-07-12
1.1.2 | Define research requirements | S. Jones | 7 | 2024-07-10 | 2024-07-17
1.1.3 | Determine in-house resource or hire vendor | J. Dow | 2 | 2024-07-15 | 2024-07-17
1.2 | Vendor Selection Phase | J. Dow | 19 | 2024-07-19 | 2024-08-07
1.2.1 | Define vendor selection criteria | J. Dow | 3 | 2024-07-19 | 2024-07-22
1.2.2 | Develop vendor selection questionnaire | S. Jones, T. Wates | 2 | 2024-07-22 | 2024-07-24
1.2.3 | Develop Statement of Work | S. Jones | 4 | 2024-07-26 | 2024-07-30
1.2.4 | Evaluate proposal | J. Dow, S. Jones | 4 | 2024-08-02 | 2024-08-06
1.2.5 | Select vendor | J. Dow | 1 | 2024-08-06 | 2024-08-07
1.3 | Research Phase | G. Lee | 47 | 2024-08-09 | 2024-09-25
1.3.1 | Develop market research information needs questionnaire | G. Lee | 2 | 2024-08-09 | 2024-08-11
1.3.2 | Interview marketing group for market research needs | G. Lee | 2 | 2024-08-11 | 2024-08-13
1.3.3 | Document information needs | G. Lee, S. Jones | 1 | 2024-08-13 | 2024-08-14
Formulas:
End = IF(AND([Days],[Start]),[Start]+[Days],"")